## Controls
Workbook Controls
Report Date | 2026-04-07
Project Statuses | Invoice Statuses | Document Statuses | Pipeline Stages | Inventory Flags
Planning | Draft | Open | Setup | OK
Active | Submitted | Pending | Procurement | Reorder
Billing | Approved | Approved | Field Install | On Order
Closeout | Partial | Closed | Testing | Issued
Closed | Paid |  | Billing
On Hold | Overdue |  | Closeout
Note on B3: Change this date to roll the dashboard and aging metrics forward.

## Project Dashboard
LINX Project Operations Dashboard
Report Date | 2026-04-07 |  | Sample dashboard for interviews — built in Excel to simulate project setup, billing, document control, inventory, and closeout tracking.
Open Projects |  |  | Total Revised Budget |  |  | Total Actual Cost |  |  | Gross Remaining |  |  | Outstanding A/R |  |  |  | Status | Count
5 |  |  | 644000 |  |  | 467300 |  |  | 176700 |  |  | 81000 |  |  |  | Planning | 1
Overdue Docs |  |  | Reorder Alerts |  |  | Open Invoices |  |  | Avg Completion |  |  | Projects Over Budget |  |  |  | Active | 2
3 |  |  | 4 |  |  | 6 |  |  | 76.17% |  |  | 0 |  |  |  | Billing | 1
[16 empty] | Closeout | 1
[16 empty] | Closed | 1
Project ID | Project Name | Office | Project Manager | Start Date | End Date | Status | % Complete | Base Budget | Approved COs | Revised Budget | Actual Cost | Cost Variance | Billed To Date | Cash Received | Outstanding AR | Project | Revised Budget | Actual Cost | Outstanding AR
P-1001 | Denver Data Center Buildout | Denver | Riley Chen | 2026-01-12 | 2026-05-29 | Active | 65% | 185000 | 18000 | 203000 | 126500 | 76500 | 118000 | 90000 | 28000 | Denver Data Center Buildout | 203000 | 126500 | 28000
P-1002 | Seattle Office Security Upgrade | Seattle | Morgan Lee | 2026-02-02 | 2026-04-24 | Billing | 92% | 72000 | 4500 | 76500 | 68100 | 8400 | 74500 | 61000 | 13500 | Seattle Office Security Upgrade | 76500 | 68100 | 13500
P-1003 | Salt Lake Wireless Refresh | Salt Lake City | Jordan Patel | 2026-02-18 | 2026-06-12 | Planning | 24% | 94000 | 0 | 94000 | 18250 | 75750 | 15000 | 0 | 15000 | Salt Lake Wireless Refresh | 94000 | 18250 | 15000
P-1004 | San Antonio Cabling Retrofit | San Antonio | Avery Brooks | 2025-12-08 | 2026-03-20 | Closeout | 98% | 128000 | 12000 | 140000 | 137900 | 2100 | 141000 | 134500 | 6500 | San Antonio Cabling Retrofit | 140000 | 137900 | 6500
P-1005 | Atlanta Access Control Install | Atlanta | Taylor Nguyen | 2026-01-27 | 2026-04-30 | Active | 78% | 86000 | 6500 | 92500 | 80100 | 12400 | 70000 | 52000 | 18000 | Atlanta Access Control Install | 92500 | 80100 | 18000
P-1006 | Cheyenne MDF/IDF Cleanup | Cheyenne | Casey Smith | 2026-01-06 | 2026-02-28 | Closed | 100% | 38000 | 0 | 38000 | 36450 | 1550 | 38200 | 38200 | 0 | Cheyenne MDF/IDF Cleanup | 38000 | 36450 | 0

## Billing Tracker
Billing Tracker & A/R Aging
Total Gross Billings |  |  | Net Billable |  |  | Cash Received |  |  | Current A/R
338700 |  |  | 311875 |  |  | 175500 |  |  | 136375
Invoice # | Project ID | Project Name | Invoice Date | Invoice Amount | Retainage % | Net Billable | Paid Amount | Payment Date | Payment Status | Days Outstanding | Aging Bucket | Aging Bucket | Open $
INV-26001 | P-1001 | Denver Data Center Buildout | 2026-02-28 | 42000 | 10% | 37800 | 25000 | 2026-03-20 | Partial | 38 | 31-60 | 0-30 | 142075
INV-26002 | P-1001 | Denver Data Center Buildout | 2026-03-31 | 38000 | 10% | 34200 | 0 |  | Submitted | 7 | 0-30 | 31-60 | 37800
INV-26003 | P-1002 | Seattle Office Security Upgrade | 2026-03-15 | 26000 | 5% | 24700 | 26000 | 2026-04-02 | Paid | 18 | 0-30 | 61-90 | 0
INV-26004 | P-1003 | Salt Lake Wireless Refresh | 2026-03-29 | 15000 | 0% | 15000 | 0 |  | Approved | 9 | 0-30 | 90+ | 0
INV-26005 | P-1004 | San Antonio Cabling Retrofit | 2026-02-18 | 47000 | 10% | 42300 | 42300 | 2026-03-28 | Paid | 38 | 31-60
INV-26006 | P-1005 | Atlanta Access Control Install | 2026-03-08 | 30000 | 10% | 27000 | 12000 | 2026-04-01 | Partial | 30 | 0-30
INV-26007 | P-1005 | Atlanta Access Control Install | 2026-04-04 | 22000 | 10% | 19800 | 0 |  | Draft | 3 | 0-30
INV-26008 | P-1006 | Cheyenne MDF/IDF Cleanup | 2026-02-11 | 18200 | 0% | 18200 | 18200 | 2026-02-25 | Paid | 14 | 0-30
INV-26009 | P-1002 | Seattle Office Security Upgrade | 2026-04-01 | 48500 | 5% | 46075 | 0 |  | Submitted | 6 | 0-30
INV-26010 | P-1004 | San Antonio Cabling Retrofit | 2026-01-30 | 52000 | 10% | 46800 | 52000 | 2026-03-05 | Paid | 34 | 31-60

## Document Control
Document Control Log
Track RFIs, submittals, and closeout documents with due dates and overdue flags. | [10 empty] | Open Items |  | Overdue Items | Closed / Approved
[11 empty] | 7 |  | 3 | 5
Doc ID | Project ID | Project Name | Document Type | Description | Date Submitted | Due Date | Status | Owner | Overdue? | Days Open
RFI-101 | P-1001 | Denver Data Center Buildout | RFI | Conduit routing clarification | 2026-03-12 | 2026-03-19 | Closed | Riley Chen | No | 7 | Status | Count
SUB-204 | P-1001 | Denver Data Center Buildout | Submittal | Cable schedule package | 2026-03-28 | 2026-04-08 | Pending | Morgan Lee | No | 10 | Open | 3
RFI-118 | P-1002 | Seattle Office Security Upgrade | RFI | Door hardware coordination | 2026-03-26 | 2026-04-01 | Approved | Jordan Patel | No | 6 | Pending | 4
SUB-208 | P-1003 | Salt Lake Wireless Refresh | Submittal | AP mounting details | 2026-04-01 | 2026-04-12 | Open | Taylor Nguyen | No | 6 | Approved | 2
RFI-127 | P-1004 | San Antonio Cabling Retrofit | RFI | Above-ceiling access request | 2026-03-05 | 2026-03-12 | Closed | Avery Brooks | No | 7 | Closed | 3
CLS-001 | P-1004 | San Antonio Cabling Retrofit | Closeout | Warranty letter draft | 2026-03-21 | 2026-03-31 | Pending | Casey Smith | Yes | 17
RFI-133 | P-1005 | Atlanta Access Control Install | RFI | Panel location confirmation | 2026-03-29 | 2026-04-03 | Open | Taylor Nguyen | Yes | 9
SUB-211 | P-1005 | Atlanta Access Control Install | Submittal | Device cut sheet package | 2026-03-30 | 2026-04-06 | Pending | Morgan Lee | Yes | 8
CLS-002 | P-1006 | Cheyenne MDF/IDF Cleanup | Closeout | As-built markup | 2026-02-18 | 2026-02-28 | Approved | Riley Chen | No | 10
SUB-198 | P-1002 | Seattle Office Security Upgrade | Submittal | Panel schedules | 2026-03-10 | 2026-03-17 | Closed | Jordan Patel | No | 7
RFI-139 | P-1001 | Denver Data Center Buildout | RFI | Rack elevation confirmation | 2026-04-02 | 2026-04-09 | Open | Riley Chen | No | 5
CLS-003 | P-1005 | Atlanta Access Control Install | Closeout | O&M draft | 2026-04-03 | 2026-04-15 | Pending | Avery Brooks | No | 4

## Inventory Tracker
Inventory & Procurement Tracker
Consumables and job-site materials with reorder automation. | [9 empty] | Stock Value |  | Items to Reorder | Items On Order
[10 empty] | 8717 |  | 4 | 1
Item ID | Item Name | Category | Location | Unit Cost | Qty On Hand | Reorder Point | Qty On Order | Reorder Flag | Stock Value
MAT-001 | Cat6A Cable Box | Cabling | Denver Yard | 185 | 12 | 8 | 6 | On Order | 2220 | Category | Stock Value
MAT-002 | Patch Panels | Hardware | Seattle Office | 140 | 4 | 6 | 8 | Reorder | 560 | Cabling | 2220
MAT-003 | Faceplates | Consumable | Atlanta Office | 3 | 175 | 120 | 0 | OK | 525 | Hardware | 1210
MAT-004 | Velcro Ties | Consumable | San Antonio Office | 12 | 15 | 20 | 25 | Reorder | 180 | Consumable | 777
MAT-005 | Security Readers | Security | Atlanta Office | 420 | 9 | 6 | 0 | OK | 3780 | Security | 3780
MAT-006 | Fiber Shelf | Hardware | Denver Yard | 325 | 2 | 3 | 2 | Reorder | 650 | Field Support | 240
MAT-007 | Ice / Water Coolers | Field Support | Salt Lake City | 48 | 5 | 4 | 0 | OK | 240 | Safety | 490
MAT-008 | PPE Kits | Safety | Seattle Office | 35 | 14 | 10 | 0 | OK | 490
MAT-009 | Labels & Heat Shrink | Consumable | Cheyenne Office | 24 | 3 | 5 | 10 | Reorder | 72

## Workflow Pipeline
Workflow Pipeline & Stage Timeline
The weekly timeline highlights the current-stage window for each project.
Project ID | Project Name | Current Stage | Stage Owner | Stage Start | Planned Finish | Actual Finish | Days in Stage | Stage Status | Next Milestone | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27
P-1001 | Denver Data Center Buildout | Field Install | Riley Chen | 2026-03-23 | 2026-04-17 |  | 15 | On Track | Begin testing 4/20 | bar: 2026-03-23 to 2026-04-13
P-1002 | Seattle Office Security Upgrade | Billing | Morgan Lee | 2026-03-24 | 2026-04-10 |  | 14 | At Risk | Submit final pay app | bar: 2026-03-30 to 2026-04-06
P-1003 | Salt Lake Wireless Refresh | Procurement | Jordan Patel | 2026-03-30 | 2026-04-24 |  | 8 | On Track | Release AP order | bar: 2026-03-30 to 2026-04-20
P-1004 | San Antonio Cabling Retrofit | Closeout | Avery Brooks | 2026-03-16 | 2026-04-09 |  | 22 | Needs Review | Finalize warranty letter | bar: 2026-03-16 to 2026-04-06
P-1005 | Atlanta Access Control Install | Field Install | Taylor Nguyen | 2026-03-17 | 2026-04-22 |  | 21 | On Track | Program readers 4/14 | bar: 2026-03-23 to 2026-04-20
P-1006 | Cheyenne MDF/IDF Cleanup | Closed | Casey Smith | 2026-02-10 | 2026-02-28 | 2026-02-27 | 17 | Complete | Archive project files